## Original
Lakeside Escapes Booking System | [5 empty] | 2023-09-01 |  |  |  | 2023-10-01 |  |  |  |  | 2023-11-01 |  |  |  | 2023-12-01 |  |  |  | 2024-01-01 |  |  |  |  | 2024-02-01 |  |  |  | 2024-03-01 |  |  |  | 2024-04-01
TASK | ASSIGNED TO | PROGRESS | START | END | DURATION | 4 | 11 | 18 | 25 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29
Requirement Phase
Review Case Study | Brooke Cunningham | 75% | 2023-09-04 | 2023-09-17 | 10
Identify Issues with Current System | Brooke Cunningham | 50% | 2023-09-11 | 2023-09-24 | 10
Identify and Document User Requirements | Brooke Cunningham | 25% | 2023-09-18 | 2023-10-01 | 10
Design Phase
Assess and Identify a Design Methodology |  |  | 2023-10-02 | 2023-10-08
Identify and Document Different Solutions | Brooke Cunningham | 25% | 2023-10-02 | 2023-10-08 | 5
Create Entity Relationship Diagram | Brooke Cunningham | 40% | 2023-10-09 | 2023-10-15 | 5
Database Normalisation | Brooke Cunningham | 60% | 2023-10-16 | 2023-10-22 | 5
Create Data Dictionaries | Brooke Cunningham | 85% | 2023-10-23 | 2023-10-29 | 5
Create UML Diagrams | Brooke Cunningham | 75% | 2023-10-30 | 2023-11-05 | 5
Create Storyboards | Brooke Cunningham | 25% | 2023-10-02 | 2023-11-05 | 25
Implementation Phase
Create Application and Database (Data Dictionaries) |  |  | 2023-11-06 | 2023-11-12 | 5
Create Graphical User Interface (Windows Forms) |  |  | 2023-11-13 | 2023-11-26 | 10
Create Classes (DALs and Models) |  |  | 2023-11-27 | 2023-12-03 | 5
Implement Guest Functionality |  |  | 2023-12-04 | 2023-12-17 | 10
Implement Booking Functionality | Brooke Cunningham | 50% | 2023-12-11 | 2023-12-24 | 10
Implement Pod Functionality | Brooke Cunningham | 50% | 2023-12-18 | 2023-12-31 | 10
Implement Reporting Functionality | Brooke Cunningham | 50% | 2023-12-04 | 2023-12-31 | 20
Verification Phase
Develop Test Plan | Brooke Cunningham | 50% | 2024-01-01 | 2024-01-14 | 10
Write Pseudocode | Brooke Cunningham | 50% | 2024-01-08 | 2024-01-21 | 10
Input/Process/Output Documentation | Brooke Cunningham | 50% | 2024-01-15 | 2024-01-21 | 5
End User Feedback | Brooke Cunningham | 50% | 2024-01-01 | 2024-01-28 | 20
Data Entry Testing | Brooke Cunningham | 50% | 2024-01-29 | 2024-02-11 | 10
Link Testing | Brooke Cunningham | 50% | 2024-02-12 | 2024-02-18 | 5
User Acceptance Testing | Brooke Cunningham | 50% | 2024-01-22 | 2024-02-18 | 20
Evaluation of Range of Approaches | Brooke Cunningham | 50% | 2024-02-19 | 2024-02-25 | 5
Evaluation of User Requirements | Brooke Cunningham | 50% | 2024-02-19 | 2024-02-25 | 5
Evaluation of Testing | Brooke Cunningham | 50% | 2024-02-19 | 2024-03-03 | 10
Evaluation of Design Methodology | Brooke Cunningham | 50% | 2024-02-26 | 2024-03-03 | 5
Evaluation of Project Management | Brooke Cunningham | 50% | 2024-02-26 | 2024-03-03 | 5
Evaluation of Solution | Brooke Cunningham | 50% | 2024-02-26 | 2024-03-03 | 5
Evaluation of Individual Performance | Brooke Cunningham | 50% | 2024-02-26 | 2024-03-10 | 10
Create Code Repository | Brooke Cunningham | 50% | 2024-03-11 | 2024-03-24 | 10
Write Developers Diary | Brooke Cunningham | 50% | 2023-09-04 | 2024-04-14 | 160
Deployment Phase
Documentation Walkthrough | Brooke Cunningham | 50% | 2024-02-12 | 2024-03-31 | 35
Write User Guide | Brooke Cunningham | 50% | 2024-02-19 | 2024-04-07 | 35

## Split
Lakeside Escapes Booking System | [5 empty] | 2023-09-01 |  |  |  | 2023-10-01 |  |  |  |  | 2023-11-01 |  |  |  | 2023-12-01 |  |  |  | 2024-01-01 |  |  |  |  | 2024-02-01 |  |  |  | 2024-03-01 |  |  |  | 2024-04-01
TASK | ASSIGNED TO | PROGRESS | START | END | DURATION | 4 | 11 | 18 | 25 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29
Requirement Phase
Review Case Study | Brooke Cunningham | 75% | 2023-09-04 | 2023-09-17 | 10
Identify Issues with Current System | Brooke Cunningham | 50% | 2023-09-11 | 2023-09-24 | 10
Identify and Document User Requirements | Brooke Cunningham | 25% | 2023-09-18 | 2023-10-01 | 10
Design Phase
Assess and Identify a Design Methodology |  |  | 2023-10-02 | 2023-10-08
Identify and Document Different Solutions | Brooke Cunningham | 25% | 2023-10-02 | 2023-10-08 | 5
Create Entity Relationship Diagram | Brooke Cunningham | 40% | 2023-10-09 | 2023-10-15 | 5
Normalisation | Brooke Cunningham | 60% | 2023-10-16 | 2023-10-22 | 5
Create Data Dictionaries | Brooke Cunningham | 85% | 2023-10-16 | 2023-10-22 | 5
Create UML Diagrams | Brooke Cunningham | 75% | 2023-10-23 | 2023-10-29 | 5
Input/Process/Output Documentation |  |  | 2023-10-30 | 2023-11-05 | 5
Create Storyboards | Brooke Cunningham | 25% | 2023-10-02 | 2023-11-05 | 25
Pseudocode |  |  | 2023-10-30 | 2023-11-05 | 5
End User Feedback |  |  | 2023-10-02 | 2023-11-05 | 25
Implementation Phase
Create Application and Database (Data Dictionaries) |  |  | 2023-11-06 | 2023-11-12 | 5
Create Graphical User Interface (Windows Forms) |  |  | 2023-11-13 | 2023-11-26 | 10
Create Classes (DALs and Models) |  |  | 2023-11-27 | 2023-12-03 | 5
Implement Guest Functionality |  |  | 2023-12-04 | 2023-12-17 | 10
Implement Booking Functionality | Brooke Cunningham | 50% | 2023-12-11 | 2023-12-24 | 10
Implement Pod Functionality | Brooke Cunningham | 50% | 2023-12-18 | 2023-12-31 | 10
Implement Reporting Functionality | Brooke Cunningham | 50% | 2023-12-04 | 2023-12-31 | 20
Verification Phase
Test Plan | Brooke Cunningham | 50% | 2024-01-01 | 2024-01-14 | 10
Data Entry Testing | Brooke Cunningham | 50% | 2024-01-29 | 2024-02-11 | 10
Link Testing | Brooke Cunningham | 50% | 2024-02-12 | 2024-02-18 | 5
User Acceptance Testing | Brooke Cunningham | 50% | 2024-01-22 | 2024-02-11 | 15
Evaluation of Range of Approaches | Brooke Cunningham | 50% | 2024-02-19 | 2024-02-25 | 5
Evaluation of User Requirements | Brooke Cunningham | 50% | 2024-02-19 | 2024-02-25 | 5
Evaluation of Testing | Brooke Cunningham | 50% | 2024-02-19 | 2024-03-03 | 10
Evaluation of Design Methodology | Brooke Cunningham | 50% | 2024-02-26 | 2024-03-03 | 5
Evaluation of Project Management | Brooke Cunningham | 50% | 2024-02-26 | 2024-03-03 | 5
Evaluation of Solution | Brooke Cunningham | 50% | 2024-02-26 | 2024-03-03 | 5
Evaluation of Individual Performance | Brooke Cunningham | 50% | 2024-02-26 | 2024-03-10 | 10
Create Code Repository | Brooke Cunningham | 50% | 2024-03-11 | 2024-03-24 | 10
Developer's Diary | Brooke Cunningham | 50% | 2023-09-04 | 2024-05-26 | 190
Deployment Phase
User Guide | Brooke Cunningham | 50% | 2024-02-19 | 2024-04-07 | 35